## Sheet1
DRAFT RATE CARD - QA
PROJECT COST | QA Hours/FTE
$10MM+ Projects | 4 FTE's at 30 hours a week each
$1MM+ Projects | 2 FTE's at 30 hours a week each
$250,000+ Projects | 1 FTE at 30 hours a week
<$250,000 Projects | 1 FTE at 20 hours a week

## Resource Estimate Summary
Project Name: | ABC Vendor Hosted Solution for Project X
Department: | Quality Services - QA
Prepared By: | James A. Hussiere
Resource Rates |  | Total Estimate by Resource |  |  | Total Estimate by PMLC Phase
Resource | Rate | Resource | Total Hours | Total Cost | PMLC Phase | Total Hours | Total Cost
QA Mgr FTE Rate | 100 | QA Manager | 16 | 1600 | Concept | 0 | 0
QA Mgr Contract Rate | 150 | QA Lead | 220 | 7000 | Initiation | 16 | 1600
QA Lead FTE Rate | 50 | QA Tester | 200 | 12000 | Planning | 80 | 4000
QA Lead Contract Rate | 75 | Total: | 436 | 20600 | Execution | 320 | 14000
QA Tester FTE Rate | 45 |  |  |  | Closing | 20 | 1000
QA Tester Contract Rate | 60 |  |  |  | Total: | 436 | 20600
Notes: | Resource rates in rate table are for illustration purposes only and do not reflect actual financials
Roles indicated are for illustration purposes only and can be updated to reflect roles defined in SDLC refinement effort
Rates are used in calculations on estimate worksheet, changes will be reflected in both worksheets
Summary by resource shows total hours and cost by role - can be split by contract and FTE
Summary by phase shows total hours and cost for QA for each phase
Terminology can be modified to reflect SDLC refinement

## Resource Estimate Worksheet
Project Name: | ABC Vendor Hosted Solution for Project X
Department: | Quality Services - QA
Prepared By: | James A. Hussiere
PMLC Phase | Concept |  |  |  |  | Initiation |  |  |  |  | Planning |  |  |  |  | Execution |  |  |  |  | Closing |  |  |  |  | Project Estimates
SDLC Phase | Concept |  |  |  |  | Initiation |  |  |  |  | Analysis / Planning |  |  |  |  | Set Up / Testing / Implementation |  |  |  |  | Post Implementation
Resource/Role | Tasks/Deliverables | Contract / FTE | Est Hours | % Allocation | Estimated Cost | Tasks/Deliverables | Contract / FTE | Est Hours | % Allocation | Estimated Cost | Tasks/Deliverables | Contract / FTE | Est Hours | % Allocation | Estimated Cost | Tasks/Deliverables | Contract / FTE | Est Hours | % Allocation | Estimated Cost | Tasks/Deliverables | Contract / FTE | Est Hours | % Allocation | Estimated Cost | Total Estimated Resource Hours | Total Estimated Resource Cost
QA Manager |  |  |  |  | 0 | Consult/Review | F | 8 | 100 | 800 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 8 | 800
[5 empty] | 0 | High Level Estimates | F | 4 | 100 | 400 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 4 | 400
[5 empty] | 0 | QA Rate Card | F | 4 | 100 | 400 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 4 | 400
QA Lead |  |  |  |  | 0 |  |  |  |  | 0 | Consult/Review | F | 20 | 50 | 1000 |  |  |  |  | 0 |  |  |  |  | 0 | 20 | 1000
[5 empty] | 0 |  |  |  |  | 0 | QA Strategy | F | 20 | 50 | 1000 | Detailed Test Management Plan | F | 40 | 75 | 2000 | Test Review | F | 20 | 25 | 1000 | 80 | 4000
[5 empty] | 0 |  |  |  |  | 0 | Test Management Plan | F | 40 | 50 | 2000 | Assist UAT | F | 80 | 75 | 0 |  |  |  |  | 0 | 120 | 2000
QA Tester |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | Test Cases | C | 80 | 100 | 4800 |  |  |  |  | 0 | 80 | 4800
[5 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 | Testing (Not UAT) | C | 120 | 100 | 7200 |  |  |  |  | 0 | 120 | 7200
Totals: |  |  |  |  | 0 |  |  | 16 |  | 1600 |  |  | 80 |  | 4000 |  |  | 320 |  | 14000 |  |  | 20 |  | 1000 | 436 | 20600
Notes: | Template can be used by managers/leads to determine resource estimates at various stages of the project
PMLC and SDLC stages indicated - SDLC phases illustrate QMM, can be tailored for each area in QS
Tasks and Deliverables indicated are based on current QMM SDLC refinement effort, can be tailored by project
Calculations are based on Contract vs FTE rates in rate table on summary tab - rates are only for illustration purposes and do not reflect actual financials
Roles indicated are for illustration purposes only and can be updated to reflect roles defined in SDLC refinement effort