## Sheet1
Phase | Activity | Methodology | Deliverable | Project Manager | Business Analyst | Solution Architect | Infrastructure Architect | Information Architect | Developer | Database Administrator | Quality Analyst | Information Security | Support Technician | Release Manager | Line of Business
Concept | Gather Stakeholder Vision | RMM | Vision Document or Project Charter | A | C | C | [8 empty] | R
Initiation |  | RMM | Risk Rate Card | A | R | R | [8 empty] | C
Initiation |  | RMM | SIPOC | R | A | [9 empty] | R
Analysis | Gather Requirements | RMM | Business Requirement Doc (BRD) | I | A | I | I |  |  |  | R |  |  |  | R
Analysis | Gather Requirements | RMM | Current State Processes | I | A | I | I |  |  |  | I |  |  |  | R
Analysis | Gather Requirements | RMM | Baseline Metrics | R | A | I | I | C |  |  | I |  |  |  | R
Analysis | Gather Requirements | RMM | Stakeholder Presentation | R | A | C | C |  |  |  | I |  |  |  | R
Analysis | Track Requirement Development | RMM | RACI | A | R | C |  |  |  |  | C |  |  |  | R
Analysis | Review Architecture | TMM | Architecture Profile |  | C | A | R | R |  |  |  | C | C |  | I
Analysis | Create Technology Approach | TMM | Solution Architecture (High Level) |  | C | A | R | R | C | C | I | R | C |  | I
Analysis | Create Technology Approach | TMM | DR Form |  | R | R | A | R |  | C | I | R | I |  | C
Analysis | Create Technology Approach | TMM | SQLServer Sizing Form |  | C | R | A | R |  | R | I |  | I
Analysis | Estimate Costs | TMM | Bill of Materials (Preliminary) | bar: A to R
Analysis | Analyze Technical Options | TMM | Solution Recommendation |  | C | A | R | R | C | C | I |  | C |  | C
Analysis | Feasibility Assessment | TMM | Bill of Materials (Preliminary) | bar: C to R; C
Develop Requirements | Refine Requirements | RMM | Future State Processes | I | [10 empty] | R | bar: C to R; I
Develop Requirements | Refine Requirements | RMM | Business Requirements Doc (BRD) | I | A | R | R | C |  |  | R | C |  |  | R
Develop Requirements |  | RMM | Use Cases | I | C: A; A: C; I: R |  | R
Develop Requirements |  | RMM | Business Rules | I | C: A; A: C; I: R; R: C |  | R
Develop Requirements |  | RMM | Stakeholder Presentation | R | C: A; A: R; R: C; I: R; R: C |  | R
Develop Requirements | Track Requirement Development | RMM | Requirements Traceability Matrix | I | A | R | C |  | C | C | R |  |  |  | I
Specification | Create Detailed Design | TMM | Solution Architecture (Detailed) |  | C | A | R | R | C | C | C |  | I |  | I
Specification | Create ETL Design | TMM | ETL Design |  | C | C |  | A | I | C | I
Specification | Refine Estimates | TMM | Bill of Materials | bar: A to R
Specification | Feasibility Assessment | TMM | Bill of Materials | bar: A to R; C
Specification | Plan Disaster Recovery | TMM | DR Plan |  | C | R | R | R |  |  | C | A | C | I | C
Planning | Define Test Environment | QMM | Quality Approach | C | [10 empty] | C | bar: C to I; C
Planning | Create Test Approach | QMM | Quality Management Plan | R | C | I | I |  | I | I | A |  | I |  | C
Planning | Verify Requirements | QMM | Identify Test Data & Environment Needs | R | C | R | C | C | C | C | A | R |  | I | C
Planning |  | QMM | Test Plan | R | [9 empty] | I | C | bar: C to R; C to C
Development | Create Application | TMM | Code |  | C | C |  | C | A | C | I |  | I
Development | Create Deployment Scripts | TMM | Deployment Scripts |  |  | I | C | I | C | C | I |  | A
Execution | Create Test Artifacts | QMM | Prepare Test Data & Environment | R | C | R | R | R | C | R | A | R | C | I | I
Execution | Create Test Artifacts | QMM | Create Test Scripts | I | C | C |  | C | C | C | A | C | C | I | I
Execution | Execute Tests | QMM | Define Defect Metrics | I | I | C | C | C | C | C | A | C | C | C | R
Execution | Unit Test | QMM | Prepare Defect Tracking Log | I |  | I |  |  | R | I | A | I | C | C | R
Execution | Track Requirement Development | QMM | Requirements Traceability Matrix | bar: I to C; C to A; R
Testing | Plan Release | TMM | Implementation Plan | R |  | I | R | I | R | R | R | R | A | R | C
Service Transition | Implementation Readiness | QMM | Implementation Checklist | I | C | R | R | R | R | R | C | R | R | A | R
Service Transition | Execute Release | TMM | Live Application | I | I | I | R | I | R | R | I | I | A | R | R
R |  | Responsible to perform the task.
A |  | Accountable for the task being completed. Only one role may be Accountable.
C |  | Consulted with. Provides input and/or review.
I |  | Informed of the outcome.
Note on L27: e1039316: Only if we are being asked to assist in the testing as sometimes occurs.
Note on L39: e1039316: In the sense that we help perform/coordinate, implementation testing and testing of apps if backed out.

## Sheet2
SDLC RACI Chart
Phase | Methodology | Deliverable | Project Manager | Business Analyst | Solution Architect | Infrastructure Architect | Information Architect | Developer | Database Administrator | Quality Analyst | Information Security | Support Technician | Release Manager | Line of Business
Concept | RMM | Vision Document or Project Charter | A | C | C | [8 empty] | R
Initiation | RMM | Risk Rate Card | A | R | R | [8 empty] | C
Initiation | RMM | SIPOC | R | A | [9 empty] | R
Analysis | RMM | Business Requirement Doc (BRD) | I | A | I | I |  |  |  | R |  |  |  | R
Analysis | RMM | Current State Processes | I | A | I | I |  |  |  | I |  |  |  | R
Analysis | RMM | Baseline Metrics | R | A | I | I | C |  |  | I |  |  |  | R
Analysis | RMM | Stakeholder Presentation | R | A | C | C |  |  |  | I |  |  |  | R
Analysis | RMM | RACI | A | R | C |  |  |  |  | C |  |  |  | R
Analysis | TMM | Architecture Profile |  | C | A | R | R |  |  |  | C | C |  | I
Analysis | TMM | Solution Architecture (High Level) |  | C | A | R | R | C | C | I | R | C |  | I
Analysis | TMM | DR Form |  | R | R | A | R |  | C | I | R | I |  | C
Analysis | TMM | SQLServer Sizing Form |  | C | R | A | R |  | R | I |  | I
Analysis | TMM | Bill of Materials (Preliminary) | bar: A to R
Analysis | TMM | Solution Recommendation |  | C | A | R | R | C | C | I |  | C |  | C
Analysis | TMM | Bill of Materials (Preliminary) | bar: C to R; C
Develop Requirements | RMM | Future State Processes | I | [10 empty] | R | bar: C to R; I
Develop Requirements | RMM | Business Requirements Doc (BRD) | I | A | R | R | C |  |  | R | C |  |  | R
Develop Requirements | RMM | Use Cases | I | C: A; A: C; I: R |  | R
Develop Requirements | RMM | Business Rules | I | C: A; A: C; I: R; R: C |  | R
Develop Requirements | RMM | Stakeholder Presentation | R | C: A; A: R; R: C; I: R; R: C |  | R
Develop Requirements | RMM | Requirements Traceability Matrix | I | A | R | C |  | C | C | R |  |  |  | I
Specification | TMM | Solution Architecture (Detailed) |  | C | A | R | R | C | C | C |  | I |  | I
Specification | TMM | ETL Design |  | C | C |  | A | I | C | I
Specification | TMM | Bill of Materials | bar: A to R
Specification | TMM | Bill of Materials | bar: A to R; C
Specification | TMM | DR Plan |  | C | R | R | R |  |  | C | A | C | I | C
Planning | QMM | Quality Approach | C | [10 empty] | C | bar: C to I; C
Planning | QMM | Quality Management Plan | R | C | I | I |  | I | I | A |  | I |  | C
Planning | QMM | Identify Test Data & Environment Needs | R | C | R | C | C | C | C | A | R |  | I | C
Planning | QMM | Test Plan | R | [9 empty] | I | C | bar: C to R; C to C
Development | TMM | Code |  | C | C |  | C | A | C | I |  | I
Development | TMM | Deployment Scripts |  |  | I | C | I | C | C | I |  | A
Execution | QMM | Prepare Test Data & Environment | R | C | R | R | R | C | R | A | R | C | I | I
Execution | QMM | Create Test Scripts | I | C | C |  | C | C | C | A | C | C | I | R
Execution | QMM | Define Defect Metrics | I | I | C | C | C | C | C | A | C | C | C | R
Execution | QMM | Prepare Defect Tracking Log | I |  | I |  |  | R | I | A | I | C | C | R
Execution | QMM | Requirements Traceability Matrix | bar: I to C; C C C to A A A; I R R
Testing | TMM | Implementation Plan | R |  | I | R | I | R | R | R | R | A | R | C
Service Transition | QMM | Implementation Checklist | I | C | R | R | R | R | R | C | R | R | A | R
Service Transition | TMM | Live Application | I | I | I | R | I | R | R | I | I | A | R | R
R | Responsible to perform the task.
A | Accountable for the task being completed. Only one role may be Accountable.
C | Consulted with. Provides input and/or review.
I | Informed of the outcome.
Note on K28: e1039316: Only if we are being asked to assist in the testing as sometimes occurs.
Note on K40: e1039316: In the sense that we help perform/coordinate, implementation testing and testing of apps if backed out.