## Document Control
Performance Test Effort Estimation
Purpose
This document is used by the Performance Test Architect to create a detailed effort estimate by filling in the cells highlighted in yellow in the corresponding worksheets. Comments have been inserted in each of these highlighted cells. This document will provide a detailed effort estimation required for project planning and scheduling purposes
Version Control
Version No. | Change History | Owner | Date
0.1 | Initial Draft | Sathish Komatireddy | 2014-07-07
0.2 | Updated with Documents control Sheet | Saleem khan | 2014-07-10
0.3 | Updated Purpose | Arijeet Sarkar | 2014-07-14
Version No. | Reviewer | Reviewer Role | Date
0.2 | Shanafelt, Garrett | Performance Test Manager | 2014-07-11
0.3 | Kelly, Kevin | QA Head | 2014-07-16
Version No. | Approver | Approver Role | Date
0.3 | Shanafelt, Garrett | PCoE Manager | 2014-07-17
0.3 | Kelly, Kevin | QA Head | 2014-07-17

## Perf Test Effort Summary
# UI Flows | 0
# Backend Services | 0
# of batch jobs | 0
Smoke Test | Yes
Isolation Load Test | Yes
Stress Test | Yes
All-in Testing | Yes
Batch Jobs Testing | No
Backend Message based Testing | Yes
User experience tests | Yes
Performance Test Effort (Person Days) | 0
Timeline | Weeks
Initiation & Planning
Preparation
Execution
Closure
Total
Assumption
Note on C2: fnfg: The count of Business flows that has User Interface
Note on C3: fnfg: The count of Back end services that need to be simulated during the test.
Note on C4: fnfg: The count of Batch Jobs that need to be included in performance testing
Note on C5: fnfg: Is smoke test required?
Note on C6: fnfg: Is Isolation test Required?
Note on C7: fnfg: Is stress test Required?
Note on C8: fnfg: Is All in test Required for this project?
Note on C9: fnfg: Is a separate test required for Batch Jobs?
Note on C10: fnfg: Does this project have message based back end testing in scope?
Note on C11: fnfg: Is user experience testing part of scope in this project?

## Perf Test Effort Phase wise
Summary
Activities | Effort (Person Hours) | Overall %age | Work in the phase
Study & Planning | 0 | #DIV/0! | Architecture Understanding, Usage patterns & Workload Analysis
Finalize Business Transaction Flows |  | #DIV/0! | Finalization & Documentation of business flows
Synthetic Transaction Scripting |  | #DIV/0! | LR Scripting
Debug & Dry Run |  | #DIV/0! | Debug, Dry Run
Performance Testing & Monitoring Tool Setup |  | #DIV/0!
Performance Test Execution |  | #DIV/0!
Documentation |  | #DIV/0! | Test Result Preparation
Performance Bottleneck Analysis & Reporting |  | #DIV/0!
Project Management & Co-ordination |  | #DIV/0! | Planning, Track queries, project issues, status reporting
Any Other Activity |  | #DIV/0!
Total Efforts | 0 | #DIV/0!
|  | Role % Involvement |  |  |  | Timeline and Effort/Wk | Planning | Preparation |  |  | Execution |  | Closure | Total Effort
Phase | Effort (PDs) | Performance Manager | Test Architect | Perf Coordinator | Test Engineer |  | WK1 | Wk2 | WK3 | WK4 | WK5 | WK6 | WK7
Initiation & Planning | 0 | 5% | 40% | 40% | 15% | Performance Manager | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Preparation | 0 | 5% | 15% | 20% | 60% | Test Architect | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Execution | 0 | 5% | 15% | 20% | 60% | Performance Coordinator | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Closure | 0 | 5% | 40% | 40% | 15% | Performance Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | [12 empty] | 0

## Perf Test Effort Calculations
Total Performance Test Script Count |  | 0 |  | Test Preparation (Person Hours)
Is Data Preparation PerfTeam's Responsibility? |  | Yes |  | Script Complexity | Preparation | Rework | Traceability | Script data | Total Preparation
Script Complexity | Percentage Breakup | Count |  | High | 0 | 0 | 0 | 0 | 0
High | 30% | 0 |  | Medium | 0 | 0 | 0 | 0 | 0
Medium | 50% | 0 |  | Low | 0 | 0 | 0 | 0 | 0
Low | 20% | 0 |  | Other | 0 | 0 | 0 | 0 | 0
Other | 0% | 0 |  | Total | 0 | 0 | 0 | 0 | 0
Total | 100% | 0
Test Execution (Person Hours) | [6 empty] | Dry Run (Person Hours)
Test Types | Yes / No | Effort | Remarks |  |  |  | Script Complexity | Effort
Smoke Test | Yes | 0 | for test scenario, monitor and environment |  |  |  | High | 0
Transaction Mix - Isolation Load | Yes | 32 | 25%, 50%, 75%, 100% load - 2 round each |  |  |  | Medium | 0
Transaction Mix - Stress | Yes | 16 | 150% load - 2 rounds |  |  |  | Low | 0
All-In Test | Yes | 32 | 2 rounds of test with all interface |  |  |  | Other | 0
Batch Jobs - EOD | No | 0 | 2 runs |  |  |  | Total | 0
Backend Message based testing | Yes | 16 | Totally 2 rounds
User Experience tests | Yes | 16 | Totally 2 rounds
Total |  | 96
Note on D2: fnfg: Count of automated scripts to be prepared
Note on D3: fnfg: Is test data creation part of performance testing team's responsibility?

## Perf Test Est Guidelines
Performance Test Estimation Guidelines
Activity |  |  | High | Medium | Low | Other | Units
Test Script Preparation |  |  | 16 | 12 | 8 | 12 | hours per script
Dry Run |  |  | 4 | 4 | 2 | 4 | hours per script
Requirements Study, Analysis, Review & Planning |  |  | 20% |  |  |  | of preparation effort
Business flow document preparation |  |  | 10% |  |  |  | of preparation effort
Test preparation Rework |  |  | 5% |  |  |  | of preparation Effort
Script Data | Support Team's Responsibility | Prepare Script data Requirements | 15% | 15% | 15% | 15% | of preparation effort
| Performance Team's Responsibility | Understand and analyze the data requirements for the Scripts | 20% | 20% | 20% | 20% | of preparation effort
|  | Script data Preparation | 25% | 25% | 25% | 25% | of preparation effort
Traceability |  |  | 5% |  |  |  | of preparation effort
Dry Run |  |  | 100% | 100% | 100% | 100% | of dry run effort
Performance Test, moniotirng Tool Setup |  |  | 24 |  |  |  | hours
Smoke Test |  |  | 4 |  |  |  | hours per execution
One Round Transaction Mix (Load / Stress) |  |  | 8 |  |  |  | hours per execution
One Round Transaction Mix (All in) |  |  | 16 |  |  |  | hours per execution
Batch Jobs |  |  | 8 |  |  |  | hours per run
Non-OLTP - Message Based testing |  |  | 8 |  |  |  | hours per execution
User Experience tests |  |  | 8 |  |  |  | hours per execution
Documentation |  |  | 15% |  |  |  | of Execution Effort
High Level Performance Bottleneck Analysis and Reporting |  |  | 25% |  |  |  | of Execution Effort
Test Management and Coordination |  |  | 20% |  |  |  | of the Total Effort attributed to other activities
Note on B9: Test data preparation effort can vary from 30% to 150% of the preparation time based on 1. Type of test data to be created 2. Mode of creating test data 3. Relationship that need to be built on that data 4. Dependencies on the test data 5. Reusability of the data