## Release Management Checklist
Project Name:
Task | Project Phase | Assigned to | Status | Completed Date | Comments
Engage with PM to ensure participation | Initiation
Add applicable milestones to the Release Calendar | Initiation
Update Forward Schedule of Change | Initiation
Provide input to the Quality Services Rate Card
Review/Approve from Release standpoint - Test Strategy | Planning
Review/Approve from Release standpoint - Requirements Documents (business, technical, functional, etc.) | Planning
Review/Approve from Release standpoint - Requirements Traceability Matrix | Planning
Review/Approve from Release standpoint - Project Schedule(s) | Planning
Review/Approve from Release standpoint - Architecture/Network Diagrams | Planning
Review/Approve from Release standpoint - Request for Release Notice | Planning
Develop Release Management Plan | Planning
Review Implementation Plan | Execution
Review Back-out Plan | Execution
Review Verification Plan | Execution
Review Rollout Communication Plan | Execution
Review Special Week 1 Procedures | Execution
Review Standard Support Turnover Plan | Execution
Review System Configuration Documents | Execution
Review Testing Completion Certificate | Execution
Review End-user Training Documentation | Execution
Review SLAs | Execution
Attend project status meeting or Stakeholder meeting | Execution
Conduct Project Release Meeting(s) | Execution
Ensure that PM has followed FNFG Change Management process | Execution
PRB Checklist | Execution
Facilitate IT Implementation go/no go meeting | Execution
Provide input to the Implementation Communication | Execution
Note on A6: fnfg: Allows for PM to estimate cost/time for Release Management resources
Note on A19: fnfg: aka: Service Transition Plan, Turn-over Docs, BAU Support Docs
Note on A21: fnfg: Required for each test phase
Note on A23: fnfg: Ensure that SLAs (both internal & external) are in place
Note on A24: fnfg: Release Management needs to be aware of the project progress and potential impact to others
Note on A25: fnfg: This is to facilitate the implementation process and transition from "project" to "production"
Note on A26: fnfg: Have all Change Order requests been made and approved?
Note on A27: fnfg: This document belongs to the PM however Release Management needs to review to ensure that everything is ready to be presented to the PRB
Note on A28: fnfg: This should be prior to the PRB meeting for go/no go
Note on A29: fnfg: Intended to incorporate any last minute communications that Release Management many want delivered

## Sheet2
Not Started
In Progress
Completed
N/A